## Sheet1
Project Cost Estimate (Done in parallel with 1.0 Project Management in WBS)
Prepared by: Project Manager | Date: |  | 12th June 2023 to 14th September 2023
| # Units/Hrs. | Cost/Unit/Hr. | Subtotals | WBS Level 1 Totals | % of Total
WBS Items
1. Project Management |  |  |  | 286800 | 45.02%
1.1 Project manager work | 3840 | 55 | 211200
1.2 Analyst work | 2160 | 35 | 75600
2. Software |  |  |  | 274600 | 43.11%
2.1 Licensed software | 500 | 20 | 10000
2.2 Software Development* | 7560 | 35 | 264600
3. Testing
3.1 Quality Tester | 2160 | 35 | 75600 | 75600 | 11.87%
Total project cost estimate |  |  |  | 637000
Assumptions | Project Team -> Analyst + Front-End&Back-End Developer + UX Designer + Quality Tester
1. This document is for cost estimation of who worked on what, it doesn't mention every use case worked on and the numerous levels of WBS items because it will be hard
3. Project Manager worked on all WBS items for 2 years | [5 empty] | 40hour/week x 4 x 24 = 3840 Units/hrs
2. Analyst worked on 1.1 Requirement Analysis & 1.2 Analysis&Design for 1 year | [5 empty] | 45hour/week x 4 x 12 = 2160 Units/hrs
4. Software Developers (Front-End&Back-End Developer+UX Designer) worked on 2.0 Software Development for 21 months | [5 empty] | 45hour/week x 4 x 21 x 2Devs = 7560 Units/hrs
5. Quality Tester worked on Testing items from 2.0 Software Development for 1 year | [5 empty] | 45hour/week x 4 x 12 = 2160 Units/hrs
6. Total Project cost estimate is what the Client (University) will pay = Benefits payed in year1 + year2 in Business case financials

## Sheet2
* Software development
Contractor labor estimate (No Labors, Only Developers) |  |  |  |  | 0
Project team member estimate (Front-End&Back-End Developer+UX Designer) |  |  | 7560 | 35 | 264600
Total labor estimate |  |  |  |  | 264600
Function point estimate | Quantity | Conversion Factor | Function Points
External inputs | 12 | 4 | 48
External interface files | 8 | 6 | 48
External outputs | 7 | 4 | 28
External queries | 8 | 4 | 32
Logical internal tables | 9 | 7 | 63
Total function points |  |  | 219
Java 2 languange equivalency value |  |  | 46
Source lines of code (SLOC) estimate |  |  | 10074
Productivity *KSLOC^Penalty (person months) | 46.7581
Total labor hours (180 hours/month) | 8416.4542
Cost/labor hour ($30/hour) | 30
Total software development estimate | 252493.6272