## Sheet1
Risk Register for Project Name
Prepared by: |  | Project Manager |  |  | Date: |  | Started 5th May 2023 and editing this document as soon as a risk is detected
No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
1 | 1 | Exceeding Time Frames of Deliverables | Deliverables Postponed | Schedule | Small Number of Developers | Overworking Developers | Project Manager organises deliverables and schedule breaks for the developers | Developers | 50% | Product will finish 2 month late | University won't have a problem with being late.
2 | 2 | Application not stable enough | Suffering from Crashes and bugs | Non-Functional Requirements | Didn't know exact percentage of stability from client | Client Feedback | Making it more Stable | Developers | 10% | No Impact
3 | 3 | Application Scalability | 2000+ Users | Non-Functional Requirements | Website not scalable | Client requested more users on website | It wasn't first mentioned by client, so it won't be done | Client | 5% | No Impact
4 | 4 | Database Failure | Connection to Databse Lost | Functional Requirements | Using a free Database Service | Users on Website overloading the Database | It took a week to regain the connection with Database | Developers | 30% | No Impact